## Master Schedule
MASTER SCHEDULE
One project = 2 sub-rows: Row 1 = Construction Period 1, Row 2 = Construction Period 2 — the Project Name and Delivery Date in columns A and G are merged as group headers for each project
Project Name | Phase | Start Date | End Date | % Complete | Status | Delivery Date | Remarks
Sukhumvit 77 Prawet Residence | Frist Fix | 2026-03-03 | 2026-04-15 | 100% | Completed | 2026-07-10
| Second Fix | 2026-06-16 | 2026-06-16 | 100% | Construction
หมู่บ้านมัณฑนา | Frist Fix | 2026-07-16 | 2026-07-30 | 0% | On Hold | -
| Second Fix | 2026-08-10 | 2026-08-13 | 0% | On Hold
สำนักงานบริษัท เอส.บี.-ซีร่า จำกัดพระราม2 | Frist Fix | 2026-03-01 | 2026-03-15 | 100% | Construction | 2026-07-01
| Second Fix | 2026-05-26 | 2026-07-10 | 90% | On Hold
Ventier courtyard ชั้น 3 | Frist Fix | 2026-06-11 | 2026-06-18 | 100% | Completed | 2026-05-29
| Second Fix | 2026-06-27 | 2026-06-29 | 100% | Completed
บ้านคุณยู้เขาใหญ่ | Frist Fix | 2027-01-05 | 2027-01-15 | 0% | On Hold | -
| Second Fix | 2026-01-20 | 2026-01-20 | 0% | On Hold
บ้านคุณอิสระ | Frist Fix | 2026-05-26 | 2026-06-15 | 100% | Completed | 2026-06-26
| Second Fix | 2026-06-25 | 2026-06-26 | 90% | Construction
S’rin House | Frist Fix | 2026-06-15 | 2026-06-25 | 90% | Construction | 2026-10-10
| Second Fix | 2026-10-01 | 2026-10-03 | 40% | Planning
บ้านคุณปุกกี้ | Frist Fix | 2026-09-10 | 2026-09-25 | 0% | Planning | 2026-11-10
| Second Fix | 2026-11-01 | 2026-11-03 | 0% | Planning
บ้านบางบอน5ซอย7 | Frist Fix | 2026-08-06 | 2026-08-15 | 0% | On Hold | 2026-11-10
| Second Fix | 2026-11-01 | 2026-11-03 | 0% | On Hold
PhanasonSamutprakhan Residence | Frist Fix | 2026-06-17 | 2026-07-03 | 30% | Construction | 2026-07-15
| Second Fix | 2026-07-06 | 2026-07-08 | 0% | Planning
P'Gummy @Sildrom Residence FL.21 | Frist Fix | 2026-06-12 | 2026-06-15 | 100% | Completed | 2026-06-15
| Second Fix | 2026-06-12 | 2026-06-15 | 100% | Completed
HUAY KWANG RESIDENCE | Frist Fix | 2026-07-31 | 2026-08-13 | 0% | Planning | 2026-10-26
| Second Fix | 2026-10-19 | 2026-10-21 | 0% | Planning
Granpix | Frist Fix | 2026-03-10 | 2026-03-19 | 100% | Completed | 2026-04-27
| Second Fix | 2026-04-08 | 2026-04-12 | 100% | Completed
บ้านคุณอู BUGAAN พัฒนาการ | Frist Fix | 2026-03-10 | 2026-03-13 | 100% | Completed | 2026-04-21
| Second Fix | 2026-03-10 | 2026-03-13 | 100% | Completed

## Summary Report
SUMMARY REPORT
One row = one project — used to build the Overview, Status, and Financial sections of the Dashboard
Project Name | Status | Overall Progress (%) | Budget (THB) | Spent (THB) | Petty Cash (THB) | Collected (THB) | Man Power (Hours) | Site Visit Days | Site Inspector | Preliminary (THB) | VO - Variation Order (THB) | VE - Variation/Omission (THB) | Contractor Name | Contract Value (THB) | Start Date | End Date | Project Manager | Remarks
Sukhumvit 77 Prawet Residence | Construction | 90% | 326786.36 | 130000 |  | 130714.544 | 12 |  | วริษฐ์ | 5198 |  |  | บริษัท เคบีเอส ซีสเต็ม จํากัด | 130000 | 2026-03-03 | 2026-03-25 |  | รอลูกค้าคอนเฟิมวันส่งมอบงาน
หมู่บ้านมัณฑนา | On Hold | 0% | 409599.64 | 41833.8 |  | 163839.856 |  |  |  | 6972.5 |  |  | บริษัทเอ.เอ็น.เอ็นจิเนียริ่งจํากัด | 139446 | 2026-06-16 | - |  | รองานโครงสร้าง
สำนักงานบริษัท เอส.บี.-ซีร่า จำกัดพระราม2 | Planning | 90% | 576317.9 | 280000 |  | 518686.11 | 20 |  | วริษฐ์ | 12045 |  |  | บริษัทเอ.เอ็น.เอ็นจิเนียริ่งจํากัด | 280000 | 2026-07-16 | 2026-03-21 |  | ส่งมอบงานวันที่ 15/07/2026
Ventier courtyard ชั้น 3 | Completed | 100% | 322961.08 | 89000 |  | 322961.08 | 7 |  | วริษฐ์ | 24166 |  | 1444 | บริษัทเอ.เอ็น.เอ็นจิเนียริ่งจํากัด | 89000 | 2026-08-10 | 2026-05-29
บ้านคุณยู้เขาใหญ่ | On Hold | 0% | 630619.2 | - |  | 252247.68 | [5 empty] | 0 |  | - | 2026-03-01 | -
บ้านคุณอิสระ | Construction | 90% | 338450.2 | 110400 |  | 135380.08 | 8 |  | วริษฐ์ | 5783 |  | 787 | นายคธาชัย จันทร์ศรี | 138000 | 2026-05-26 | 2026-06-26 |  | รอลูกค้าคอนเฟิมวันส่งมอบงาน
S’rin House | Construction | 60% | 1156111.18 | 84000 |  | 462444.472 | 6 |  | วริษฐ์ | 26094 |  | 46175 | นายคธาชัย จันทร์ศรี | 280000 | 2026-06-11 | 2026-10-10
บ้านคุณปุกกี้ | On Hold | 0% | 594114 | 0 |  | 237645.6 |  |  |  | 20261 |  | 20018 | บริษัท เคบีเอส ซีสเต็ม จํากัด | 233247.9 | 2026-06-27 | 2026-11-10 |  | รองานโครงสร้าง
บ้านบางบอน5ซอย7 | On Hold | 0% | 327102.8 | 36000 |  | 130841.12 | 3 |  | วริษฐ์ | 14327 |  | 4164 | บริษัท สามที เอ็นจิเนียริ่ง จำกัด | 120000 | 2027-01-05 | 2026-11-10 |  | รองานโครงสร้าง
PhanasonSamutprakhan Residence | Construction | 20% | 1707089 | 197003.709 |  | 682835.6 | 6 |  | วริษฐ์ | 54190 |  | 20695.97 | บริษัทเอ.เอ็น.เอ็นจิเนียริ่งจํากัด | 656679.03 | 2026-01-20 | 2026-07-15
P'Gummy @Sildrom Residence FL.21 | Completed | 100% | 80000 | 40000 |  | 80000 | 4 |  | วริษฐ์ | 0 |  | 0 | บริษัท สามที เอ็นจิเนียริ่ง จำกัด | 40000 | 2026-05-26 | 2026-06-15
HUAY KWANG RESIDENCE | Planning | 0% | 1199960.02 | 0 |  | 479984.008 | [5 empty] | 34414 | บริษัท เคบีเอส ซีสเต็ม จํากัด | 430000 | 2026-06-25 | 2026-10-26 |  | รองานโครงสร้าง
Granpix | Completed | 100% | 600000 | 234861 |  | 600000 | 10 |  | วริษฐ์ |  |  |  | บริษัท อาร์ทอพ แอร์ ซัพพลาย จำกัด | 234861 | 2026-06-15 | 2026-04-27
บ้านคุณอู BUGAAN พัฒนาการ | Completed | 100% | 317648 | 119980 |  | 317648 | 10 |  | วริษฐ์ |  |  |  | บริษัท เคบีเอส ซีสเต็ม จํากัด | 119980 | 2026-06-27 | 2026-04-21
Formulas:
Start Date = '[1]Master Schedule'!C5

## Site Visit Log
SITE VISIT LOG
Optional sheet — one row = one team member's site visit hours in one month. Powers the team-wide Monthly Site Visit Overview chart on the Dashboard (not tied to a specific project).
Month | Inspector Name | Site Visit Hours
2026-06-12 | ฤทธิพร บุตรนิตย์ | 4
2026-06-16 | ฤทธิพร บุตรนิตย์ | 4
2026-06-10 | ธนทร วัฒนชโนบล | 3
2026-06-12 | วริษฐ์ ยุวโชติพันธุ์ | 2.5
2026-06-17 | ฤทธิพร บุตรนิตย์ | 3
2026-06-17 | วริษฐ์ ยุวโชติพันธุ์ | 3
2026-06-19 | ฤทธิพร บุตรนิตย์ | 3